# State of California Department of Fish and Wildlife **Memorandum**

**Date:** April 2, 2024  
  
**To:** Melissa Miller-Henson  
 Executive Director  
 Fish and Game Commission  
  
**From:** Charlton H. Bonham  
 Director  
  
**Su****bject:** **Proposed Marine Protected Area Petition Evaluation Process and Timeline**

At their February 14-15, 2024, meeting, the California Fish and Game Commission (CFGC) referred 20 Marine Protected Area (MPA) regulation change petitions to the California Department of Fish and Wildlife (CDFW) for review, evaluation, and recommendation. In addition, the CFGC requested CDFW develop a proposed approach to evaluate the petitions to discuss at the Marine Resources Committee (MRC) meeting on March 19, 2024. After discussion and input from interested stakeholders, the MRC recommended approval of CDFW’s proposed 3-phase approach to evaluate MPA petitions. The proposed approach is briefly described below and in the enclosed presentation that was provided to the MRC on March 19, 2024.

**Proposed 3-Phase Approach to MPA Petition Evaluation**

**Phase 1:** Petitions will be categorized into two binsusing the criteria outlined below to determine which petitions can be evaluated in the near-term and which petitions will require additional policy guidance, information, and/or resources prior to evaluation.

* **Bin 1 petitions:** Petitions that can be evaluated in the ***near-term*** must meet all the following criteria:
  + Policy direction not needed for next phases.
  + Within CFGC authority.
  + Immediate evaluation possible.
  + Limited clarification needed from petitioner.
  + Limited controversy anticipated.
* **Bin 2 petitions:** Petitions that do not meet all the above criteria will be categorized into Bin 2. The analysis of these petitions will be more complex as they will require additional policy guidance, information, and/or resources before they can be evaluated. Due to the complexity of these petitions, these will be evaluated in the ***longer term***.

**Phase 2:** Separate all Bin 1 petitions into individual actions and proceed to phase 3. Separate Bin 2 petitions into individual actions and identify additional policy guidance, information, and/or resources that are necessary to advance individual actions to phase 3.

**Phase 3:** Adaptive management evaluation and recommendations.Apply the evaluation framework approved by the CFGC to each petition action. The process will identify which petitions, and/or actions within each petition, would be recommended to be granted, denied, or considered through an alternative pathway.

**Proposed MPA Petition Evaluation Anticipated Timeline**

* **March-April 2024: Development of Evaluation Framework**
  + Receive and discuss proposed 3-phase evaluation process at the March 19 MRC and April 17 CFGC meetings.
* **April-August 2024: Phase 1— CDFW Sort Petitions into 2 Bins**
  + Discuss proposed bins at the July 18 MRC and August 14 CFGC meetings.
* **August 2024 and beyond: Phases 2 and 3—Separate petitions into individual actions** 
  + Receive guidance on Bin 2 actions as needed.
  + Move forward with evaluation on both Bin 1 and 2 actions. Evaluation timelines for Bin 1 and Bin 2 actions will vary.

If you have any questions or need more information, please contact Dr. Craig Shuman, Marine Regional Manager, at (805) 568-1246.

Attachment 1: Proposed Marine Protected Area Petition Evaluation presentation.

Attachment 2: Evaluation Framework

ec: Jenn Eckerle, Deputy Secretary for Ocean and Coastal Policy Natural Resources Agency

Craig Shuman, D. Env., Region Manager  
Marine Region

Becky Ota, Environmental Program Manager  
Marine Region

Stephen Wertz, Senior Environmental Scientist  
Marine Region

Sara Worden, Environmental Scientist

Marine Region