## Current projects
Number | Project | Science Strategy Topic | In Workplan? | PI/contact | Email | Partners | Status | Projected Timeline | Notes
1 | Climate Change MAST | Climate Change | Yes | Sam Bashevkin, Denise Colombano | Sam.Bashevkin@Waterboards.ca.gov | USGS, USBR, CDFW, DWR, USFWS | ongoing | Analysis of turbidity on hold, proposal in for analysis of change in body size of fish and inverts | working on other water quality changes over time (turbidity, salinity), then may pivot to biological changes
9 | ITAG - project workteam for acoustic telemtry coorindation | Salmonids | No | Flora Cordelioni | flora.cordoleani@noaa.gov | CDFW, NOAA Fisheries | ongoing | Annual updates | https://oceanview.pfeg.noaa.gov/shiny/FED/CalFishTrack/
11 | NMFS life-cycle model | Salmonids | No | Eric Danner | https://www.fisheries.noaa.gov/contact/eric-danner-phd |  | ongoing |  | https://swfsc.noaa.gov/ChinookLCM/
12 | CVPIA's Science Integration Team (SIT) | Salmonids | No | Lisa Elliott/Alex Vaisvil | lelliott@usbr.gov; avaisvil@usbr.gov |  | Ongoing |  | This effort was designed to prioritize CVPIA work, integrate survey data to parameterize life-cycle models
18 | Suisun Marsh Salinity Control Gates | Flow Alteration, smelt | Yes | Rosemary Hartman | Rosemary.Hartman@water.ca.gov | USBR, DWR, CDFW | ongoing | Annual updates, May of each year following an action. | Folded into the Summer-Fall habitat action DCG stuff. Baseline monitoring until we have better water year
25 | SacSewer's Operation Baseline work. | Foodwebs, contaminants | No | David Senn, Tim Mussen; Tamara Kraus, Brian B. Megan Young |  | DSP, USGS, Regional SAN | post upgrade work now | Unknown | Lots of elements are continuing. Multiple papers/projects. Isotope paper: https://www.sciencedirect.com/science/article/abs/pii/S0048969721066705?via%3Dihub
35 | Spring-Run JPE | salmon | No | Pete Nelson, Brett Harvey | Peter.Nelson@water.ca.gov | DWR, CDFW, NMFS, USFWS, USBR, Metropolitan | In progress | New extended timeline: Draft JPE Approach: June 2025 Independent Peer Review: Jan 2026 Implementation: WY 2027 | Working on database for data integration. Additional data collection efforts udnerway. https://escholarship.org/uc/item/59v4k4k3
36 | Ludwigia project | Invasive weeds | Yes | Shruti Khanna | Shruti.Khanna@wildlife.ca.gov | USGS, CDFW, UC Davis, UC Merced | Almost done | One manuscript published, one near complition, two a little further out. | a. Manuscript on effect of water primrose persistence and shape of marsh on marsh vulnerability to invasion (Morrison et al), i. (SHOULD BE SUBMITTED THIS BY THE END OF THIS MONTH - The NASA proposal/award etc. derailed the timeline on that one) b. Manuscript on allelopathic potential of water primrose in aquatic and marsh habitat (Drexler et al - published - https://doi.org/10.1007/s10530-024-03412-4 ) c. The third and fourth will be on plant traits manifested in terrestrial habitat that are different than the aquatic mats of water primrose and an eDNA paper on the diversity of marshes being invaded by water primrose. T i. (The third paper is being led by Erin Hestir and will likely not be ready for another six months. The fourth paper depends on a grad student as UCSC and we kind of have no control over that.)
37 | Longfin Smelt Science Plan | smelt | No | Brian Schreier | Brian.Schreier@water.ca.gov | DWR, CDFW | in progress | Plan complete, starting implementation. Timeline varies by action. | https://water.ca.gov/-/media/DWR-Website/Web-Pages/Programs/State-Water-Project/Files/ITP/ITP-Longfin-Science-Plan_SWP_12232020_-FINAL.pdf
39 | NCEAS workshop (2021) | food webs (2021) | No | Pascale Goertler, Sam Bashevkin | Pascale.Goertler@water.ca.gov | DSP, DWR, USBR, USFWS, CDFW, UC Davis, UC Berkeley | Almost done | Food web manuscript published. Connectivity paper submitted | Working groups met for 3 weeks in fall of 2021. Two synthesis projects were initiated, one on the connectivity of food resources with hydrology and another on the environmental and biotic drivers of food supply for fishes. Two ms will/have been submitted from 2021
39.5 | NCEAS workshop (2023) | multi-benefit approaches to managing the Delta as a social-ecological system (2023) | No | Miranda Tilcock, Xoco Shinbrot | Miranda.Tilcock@deltacouncil.ca.gov | lots | in progress | Results should be completed by end of 2024, with manuscripts submitted for publicaiton in 2025 | 2023 has also split into two synthesis projects, one on restoration and the other water infrastructure. Groups from the 2021 and 2023 cohorts presented their results at BDSC. The 2023 groups are still a work in progress but getting there!
40 | Restoration synthesis | Food webs/habitat | No | Dylan Chapple | Dylan.Chapple@deltacouncil.ca.gov | DSP, CDFW | Nearing completion | Submitted to SFEWS, currently working on major revisions to re-submit in late 2024/early 2025 | Describes statust of habitat restoration in the Delta as per the Delta Plan targets
42 | Salmon salvage model | salmon | Yes | Jereme Gaeta | Jereme.Gaeta@Wildlife.ca.gov | CDFW, ICF, Trinh and Brian Mahardja | in progress | Unknown | Delayed a bit, but Jereme is still working on it in his new position. Trinh and Brian are also helping to get it wrapped up.
44 | Delta Adapts project | Climate change | No | ? | climatechange@deltacouncil.ca.gov |  | in progress | Adaptation plan will go to public review in 2024, finalized in spring 2025 | finishing up climate vulnerability assessment, starting adaptation strategy
46 | Phytoplankton synthesis (integration project) | Food webs | Yes | Sarah Perry | Sarah.Perry@water.ca.gov | USGS, DWR | in progres | Integrated dataset should be finished sometime in 2025 | Close to having all the datasets standardized.
49 | Delta Coordination group Structured Decision Model | Flow Alteration, smelt | No | Rosemary Hartman | Rosemary.Hartman@water.ca.gov | Reclamation, CDFW, USFWS, Contractors, NMFS | Ongoing | Annual updates | This model uses habitat modeling and bioenergetic modeling to asses potential summer fall delta smelt habitat actions, included SMSCG operation, NDFA, and Ship Channel actions.
51 | Understanding within-and-between basin migration in white sturgeon: a synthesis of more than ten years of acoustic tagging data | Other native fish | No | Myfanwy Johnston, Dylan Stern | myfanwy.johnston@fishsciences.net | DSP | Almost done | Manuscript in review as of fall 2024. | Draft manuscript in pre=print - https://www.biorxiv.org/content/10.1101/2022.08.31.505999v1
52 | Standard operating procedure for diagnosing and addressing predator detections in salmon telemetry data | food webs, salmnids | No | Rebecca Buchanan; Russ Perry, Dylan Stern | dylan.stern@deltacouncil.ca.gov | DSP | in progress | Expires 6/30/25 | Work continues on the R package, data analysis, final SOP, and manuscript
53 | Spring-Run JPE at Chipps | Salmonids | No | Russ Perry/Maraiah Meek | dylan.stern@deltacouncil.ca.gov | DSP | in progress | Working on contract amendments as of fall 2024 | The goal of this project is to estimate abundance and run timing of juvenile spring-run Chinook salmon leaving the Delta at Chipps Island by leveraging two existing studies that use the latest advances in genetic and acoustic telemetry technology. 3 parts to get estimate of run-specific abundance:o Acoustic Tags, o Coded Wire Tag catch and trawl efficiency, o Trawl catch and Genetic ID. • Extension requested of approximately 6 months due to the time required to compile, process, and QAQC existing genetic assignment data.• Extracted and genotyping DNA from 800 archive tissue samples
54 | Changes in organic carbon and food resources in response to historical events in the Sacramento-San Joaquin Delta | Food webs/habitat | No | Christina Pondell (VIMS)/Dylan Chapple | Dylan.Chapple@deltacouncil.ca.gov | DSP | Almost done | Manuscript in review as of fall 2024.
55 | CV Salmon Science Synthesis | Salmonids | No | Brett Harvey | Brett.Harvey@water.ca.gov | UC Davis, UC Santa Cruz, UC Berkeley, NOAA Southwest Fisheries Science Center, DWR | in progress | Goal: draft manuscript early 2025 | This synthesis is examining new scientific information from a landscape and life cycle perspective to tell an updated story of “what’s going on with CV salmon ”. The story incorporates updated understanding (and questions) regarding how interactions of salmon population structure, climate variation, water management infrastructure and actions, temperature, flow, predation, habitat, hatcheries and harvest influence the life history diversity of CV Chinook at different life stages, and how these stressors currently affect the abundance, stability and resilience of populations. We are using this information to construct a vision of how to build resilience in the now frail CV salmon system.
56 | Zooplankton Monitoring Design Review: Gaps, Strengths, and Redundancies | Food webs | Yes | Dan Ellis | Daniel.Ellis@Wildlife.ca.gov | Rosemary Hartman, Sam Bashevkin, Kristi Arend | in progress | Hopefully wrapped up by June 2025 | Representitive species chosen, power analysis mostly done, redundance analysis starting.
57 | SAV niche model | Invasive species | Yes | Shruti Khanna | Shruti.Khanna@wildlife.ca.gov | Dan Ellis, Nick Rasmussen | Just starting | Paused to compelte other projects | Paused until some other projects get wrapped up.
59 | State of Bay-Delta Science (2024) | Climate change | No | Maggie Christman | Maggie.Christman@deltacouncil.ca.gov | DSP | in progress | Papers to be submitted by mid 2024 published sometime in 2025 | Topic area will be extreme events and include chapters on droughts, floods, heat waves, forest fires, and management governance. Drafts have been submitted for most of the chapters
60 | Fish Catchability synthesis for long-term IEP surveys | Salmonids, smelt, cyprinids, Green and White Sturgeon, food webs, invasive species (other) | No | Brock Huntsman | bhuntsman@usgs.gov | Sam, Brian | In progress | Working on manuscript revisions, should be done by end of 2024 | Completed the final objective of the effort (abundance estimates using catch-ratios) and have a full draft manuscript written. I have been going through revisions (slowly) with co-authors Brian and Sam
61 | Smelt Cage study synthesis | Delta Smelt | No | Brittany Davis | Brittany.E.Davis@water.ca.gov | Shawn acuna, Nan Fangue, Swee Teh | In progress | Manuscript resubmitted Oct 2024 | Integrating data from all the 2019 cage studies to make inferences about general patterns.
63 | Sacramento Ship Channel Synthesis | Delta Smelt | No | Rosemary Hartman | Rosemary.Hartman@water.ca.gov | Kristi Arend, Steve Sardo, Matt Young, Adrianne Smits, Brock Huntsman | in progress | Planning to complete most work by June of 2025. | Bioenergetic modeling to test hypotheses on why the ship channel is so good for smelt
64 | Large fish synthesis | fish | yes | ? | ? | Rosemary Hartman, Jim hobbs | proposed | Not developed yet | look at existing gill net and efishing datasets in the delta to see what we can and can't say about distribution and abundance of large fishes
65 | Trait based analysis of community responses to drought | Climate change | no | Dave Bosworth, nick Rasmussen, Pete Nelson | Nicholas.Rasmussen@water.ca.gov | Leela Dixit, Peggy Lehman, Christina Burdi | in progress | Trait dataset should be published to EDI by the end of 2024. | Looking at whether certain traits in fish, vegetation, phytoplankton or inveretbrates make them more resilient to drought. Results are not as promising as hoped, unsure of manuscript timeline.
66 | Longfin life cycle model | fish | no | Vanessa Tobias | vanessa_tobias@fws.gov | Brian Schreier, Scott Meyer, Mike Eakin | in progress | Building datasets and developing model through June 2026, Model to be complete by June 2027 | Part of longfin science plan
67 | Tidal Wetland State of the Science | habitat | no | Denise Colombano | denise.colombano@deltacouncil.ca.gov | Matt Young | Proposed | Starting January of 2025 | A literature review as an update to Brown 2003
68 | CSAMP Salmon Reorienting to Recovery models | salmonids | No | Alison Collins | ACollins@mwdh2o.com | CAMT, Trout Unlimited, DWR, CDFW, NMFS | In progress | Currently applying models to scenarios | https://csamp.baydeltalive.com/recovery/reorienting-to-recovery The R2R technical team adapted the Central Valley Project Improvement Act Science Integration Team (SIT) Decision Support Models (DSMs), existing life cycle models that leverage the best available research to predict annual Chinook salmon population trends across the Sacramento and San Joaquin Delta watershed. While the SIT DSMs primarily focus on habitat-specific management actions, the updated R2R life cycle models integrate data on habitat, hydrology, hatcheries, and harvest to provide a more holistic view of salmonid responses to restoration and management actions. The adapted life cycle models predict that biological recovery of fall-run Chinook salmon can be achieved through a combination of actions addressing the four Hs. These findings show that salmonid recovery is possible and outline the combinations and scale of management actions necessary to get there. The R2R portfolio of actions and models provides a roadmap for salmonid management in the Central Valley. R2R’s continued commitment to transparency and accessibility of the tools we develop will allow these models and suite of management actions to be utilized widely, which we hope will support sustained and collaborative conservation efforts now and into the future.
19 | North Delta Flow Action Synthesis | Flow Alteration, smelt | Yes | Britt Davis | Brittany.E.Davis@water.ca.gov | DWR | Wrapping up | Report completed, manuscript to be submitted soon. -Contaminants manuscript ready to submit to SFEWS, -multidisciplinary NDFS synthesis manuscript nearly completely, delays with personnel changes, but close. -plan to submit both in hopes to be included in same issue. -nutrient synthesis report has been completed in collaboration with SFSU. A manuscript will depend on capacity -stable isotope paper anticipated in 2025
69 | Wetland food web modeling | habitat | proposed | Rosemary Hartman | Rosemary.Hartman@water.ca.gov | everyone | proposed | Data integration through end of 2025, modeling and writing through end of 2026 | This project is a response to the Delta ISB's call for use of quantitative food web models to answer management questions. The team hopes to provide a framework for modeling numerous food web related questions by starting with tidal wetland benefits for fishes.
70 | Summer-fall habitat synthesis | Flow Alteration, smelt | no | Rosemary Hartman | Rosemary.Hartman@water.ca.gov | Reclamation, CDFW, USFWS, Contractors, NMFS | proposed | Data analysis an dmodeling through May of 2025, report by october of 2025 | Analyzing all summer-fall habitat actions (X2 and SMSCG) from 2011-2024 in light of recent life-cycle model results
71 | Zooplankton drivers project | Food webs | No | Rosemary Hartman | Rosemary.Hartman@water.ca.gov | Nick Rasmussen, Christina Burdi, Calvin Lee, Michelle Jungbluth | in progress | Manuscript complteed by end of 2024 | Looked at whether chlorophyll is a good predictor of zooplankton abundance and how zooplankton community structure has changed over time. Also literature review of dat aon other zooplankton food sources.
72 | Flow/nutrients/algal blooms | Flow Alteration, food webs | No | Laura Twardochelb | Laura.Twardochleb@Waterboards.ca.gov | Ellen Preece, Silvia Angles | proposed |  | to possibly examine how flow affects nutrients and other env. factors that could affect algal blooms, as well as how the env. factors affect the algal blooms themselves
73 | Winter-run survival and water operations in the Delta | salmonids | No | Alexander Jensen | alexander.jensen@noaa.gov | Brian Mahardja, Josh Israel | in progress | Draft ms essentially complete. Final edits being done before submission
74 | Six-agency redesign | everything | No | Brian Schreier | Brian.Schreier@water.ca.gov | USBR, DWR, CDFW, USFWS, NOAA Fisheries, State Board | in progress | Plans for more evaluations of surveys in 2025, but waiting for direction from the Management Committee | Analysis of FMWT spatial sampling led to increased stations in Suisun Marsh. Currently looking at spatial balance and overlap of Bay Study and FMWT
75 | Changing Paradigms of Knowledge Production: Interweaving Traditional Knowledge and Predominant Science in the Delta |  | No | Xoco Shinbrot | xoco.shinbrot@deltacouncil.ca.gov |  | in progress | Manuscript completed by end of 2024 | Paper submitted to SFWS fall of 2024
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lisa retired, need a new contanact

## Completed or paused projects
Number | Project | Science Strategy Topic | In Workplan? | PI/contact | Partners | Status | Notes
1 | Climate Change MAST, (including Brit and Cat's Temperature synthesis, plus Sam and Brian's discrete analysis) | Climate Change | Yes | Larry Brown, Cat Pien, Sam Bashevkin | USGS, USBR, CDFW, DWR, USFWS | Done | Final paper submitted, three others published. https://doi.org/10.1007/s10750-022-04886-w, http://dx.doi.org/10.15447/sfews.2022v20iss2art1, https://doi.org/10.1002/lno.12027, https://doi.org/10.1002/lno.12057
4 | Climate change on the Yolo Bypass, inundation extent. | Climate Change | No | Larry Brown and Marisa Wulff and Brock Huntsman | DWR, USGS | done | Manuscript about to be submitted. The projected water temperature modeling paper was accepted with minor revisions in SFEWS a few weeks ago (I haven't addressed comments yet), and a paper on salmon production in response to projected Yolo Flows in response to the notch has been completed and will be submitted to journal once I get internal USGS approval. Data published: https://www.sciencebase.gov/catalog/item/6089db1cd34ef6cfc4a88f4c
6 | EDSM to improve Chinnok Salmon monitoring | Salmonids | Yes | Brian Mahardja | USFWS, USBR | Done | https://escholarship.org/uc/item/9sp7r7q4
10 | Synchrony of native fish movements: Central Valley Acoustic telemetry | Salmonids/sturgeon | No | Andrew Rypel/Louise conrad | Kansas University, USBR, Uof W, USFWS, USGS. | Done | https://esajournals.onlinelibrary.wiley.com/doi/full/10.1002/ecs2.4139
15 | Biotic homogenization study | Other native fish | Yes | Ryan McKenzie/Brian Mahardja | Ryan McKenzie - NOAA Federal <ryan.mckenzie@noaa.gov>; Gredzens, Christian@USFWS <christian_gredzens@fws.gov> | Done | https://escholarship.org/uc/item/4507774x
16 | Cyprinid synthesis | Other native fish | No | Eric Huber/ Adam Nanninga | USFWS, CDFW | Paused | Originally Adam Nanniga took this over with the resident fishes PWT. However, due to multiple PWT members backing out, the project is now a USFWS project with support from CDFW. Due to funding and staffing limitations the project is currently on hold. We hope that an early career scientist in the Lodi FWS office will turn the project into a Master's thesis. We are also open to post docs or universisty graduate students taking on the project. Please let us know of any potential takers.
17 | FLOAT MAST | Flow Alteration, smelt | Yes | Rosemary Hartman | EVERYONE | Done | 2017 report is done, white papers done. Integrating into summer-fall habitat action
21 | Directed Outflow Project | Flow Alteration, smelt | Yes | Grace Easterbrook, Brian Mahardja | Easterbrook, Grace K <geasterbrook@usbr.gov> | USBR | Complete | Outflow sampling completed, shifting focus to work on turbidity maxima | Integrating into Summer-fall habitat action.
22 | Phytoplankton synthesis (EMP data only) | Foodwebs | No | Peggy Lehman | DWR | Done | https://doi.org/10.1016/j.ecss.2022.107988
23 | SFEI's work on carbon contribution of different groups, including bioavailability calculations | Foodwebs | No | Lydia Vaughn <lydiav@sfei.org> | SFEI, DSP, USGS | Done | https://doi.org/10.1016/j.scitotenv.2021.147097
26 | Zooplankton synthesis | Foodwebs | Yes | Sam Bashevkin | DSP, CDFW, DWR | Done | Tech report almost published, dataset is published, several papers published, symposium Oct 27-28 2020 was a success. Some ongoing analysis in separate projects https://doi.org/10.15447/sfews.2021v19iss3art1 https://doi.org/10.1371/journal.pone.0265402
29 | Landscape Efficacy Analysis for aquatic vegetation control | Invasive Weeds | Yes | Shruti Khanna | CDFW, UC Davis, DBW | Done | White paper completed. Sav paper is being revised to resubmit. FAV is ongoing.
30 | SAV control Resiliency Strategy Study | Invasive Weeds | Yes | Louise Conrad/Nick Rasmussen | DSP, DWR, DBW, CDFW | Done | The landscape scale efficacy analysis for SAV is complete. The paper is in second/third review at Biological Invasions. And the FAV efficacy manuscript is in writing. After that manuscript is submitted, this project is basically complete.
31 | Wakasagi synthesis | Invasive species (other) | No | Britt Davis | DWR, USBR, USFWS, CDFW | Done | https://doi.org/10.15447/sfews.2022v20iss3art2
32 | Nutria forecasting | Invasive species (other) | Yes | Vanessa Tobias | CDFW, DWR, USFWS | On hold/folded | The initial habitat models I made were ok, but they mostly just produced maps of where wetlands are because of the way the trapping locations were chosen.
33 | Lamprey synthesis | Other native fish | No | Pascale Goertler |  | Done | Pascale's original amneocyte synthesis finished up, but newer project with Chris Parker looking at juveniles, Lauren Damon may be working on something with salvage, and Grace Auringer/Mandi Finger/Matt Campbell/Pascale have submitted a ms on population structure.
38 | Steelhead synthesis | Salmonids | No | Bryan Mathias, Mike Beakes | USBR, USFWS | Done | Gap analysis from 2020 steelhead workshop complete. Papers coming. https://deltacouncil.ca.gov/pdf/science-program/fact-sheets/2021-02-03-monitoring-steelhead-populations-monitoring-and-research-gap-analysis.pdf
41 | State of Bay-Delta Science | Aquatic vegetation | No | Maggie Christman | DSP | Done | https://escholarship.org/uc/jmie_sfews/20/4
47 | Drought Synthesis (2021) | Climate Change, flow alteration | Yes | Rosemary Hartman | everyone | Done | Tech report complete, papers for special issue of sfews in revision.
50 | SAV data integration work | invsive species | No | Nick and Shruti | DBW, SePro | Done | https://portal.edirepository.org/nis/mapbrowse?packageid=edi.1376.1
45 | CSAMP Delta Smelt Structured Decision model | Smelt | No | Mike Beakes | USGS, USBR, CDFW, DWR, Contractors, USFWS, NMFS | Finished | , CAPT on pause fo rnow
48 | Seasonal Monitoring Report | Everything | No | Rosemary Hartman | DWR, CDFW, USFWS | On pause. | No one seems to really care about it or loook at it, so i'm putting it on pause. https://interagencyecologicalprogram.github.io/Status-and-Trends/
27 | Contaminants PWT Resiliency Strategy | Contaminants | No | Shawn Acuna | DWR, CDFW, DPR, Met | On hold | Looking at integrating this effort with the CSAMP SDM effort
28 | Western Washington University relative risk analysis for contaminants | Contaminants | No | Wayne Landis, Tricia Lee, Shawn Acuna | DWR, CDFW, DPR, Met | On hold | Modeling is almost done, but has been delayed. https://wp.wwu.edu/toxicology/research/
43 | Long-term monitoring program reviews | Smelt | Yes | Steve Culberson | Steve.Culberson@deltacouncil.ca.gov | DSP, USGS, CDFW, | IEP review paused, 6-agency redesign ongoing.
62 | Tidal Wetland synthesis | habitat | No | Stacy Sherman | Stacy.Sherman@wildlife.ca.gov | Christy Bowles, Rosemary Hartman | on hold |  | 5-year review of FRP data on tidal wetlands
20 | Longfin Smelt MAST | Smelt | Yes | Christina Burdi, Randy Baxter | Christina.Burdi@water.ca.gov | DWR, CDFW, USFWS | WE decided it wasn't worth finishing up because it is already outdated.
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Species status assessment from the listing descision might do the sme thing.
Note on E22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need a new contact

## New Ideas
Idea | Proposed by | Notes
Impact of drought on salmon across their life cycle | Rachel Johnson, Erin Foresman | There are a lot of needs for salmon synthesis flying around with the reconsultation, VA's etc. Putting a pause on this
Integrated data set of fish diets | Predation PWT | This will be difficult to standardize, but Tyler Pilger and Jeff are interested.
Invasive fishes | Stakeholders team (Shawn Acuna) | No clear questions
Invasive shrimp | Rosie | No clear questions, but shrimp are the top catch in the FMWT. WHAT ARE THEY DOING?
Impact of wildfire smoke on primary production | Rosie | I still want to do this.
Large fish | Fred Feyrer | We should put together all the existing efishin data and gill net data before starting a new gill net survey
Food web modeling of tidal wetlands | Delta ISB
Summer Fall Habitat Aciton | Delta Coordination Group